## Sheet 1 - Product Backlog
Product Backlog
Issue key | Summary | Description | Assignee | Status | Comments | (Story point estimate) | Sprint
NY4-57 | Create GET Model Inference | User Story: * As a job seeker, I want the platform to generate job recommendations based on my resume’s content, so that I can see how well I match open roles. Acceptance Criteria: * A GET endpoint /model-inference accepts a resumeID as part of a body. * The resume is fetched and passed to the ML model for inference. * The response contains a list of job IDs and their respective match scores. * Model inference is completed and returned. Benefit/Value: * Makes the recommendation process feel intelligent and dynamic, helping users feel seen and understood by the system. | Sarah Wierzbicki | Done |  | 3 | Sprint 2
NY4-56 | Create POST Process Resume | User Story: * As a job seeker, I want the app to process my uploaded resume and return job matches, so that I can start browsing job options personalized to my background. Acceptance Criteria: * A POST endpoint /process-resume accepts file uploads via multipart/form-data. * Resume content is extracted and passed to the ML model. * The endpoint returns a JSON response containing a resumeID and a list of matched jobs. * Validation is included for file format and size. * Errors return appropriate status codes with user-friendly messages. Benefit/Value: * Allows users to initiate their personalized job search instantly through a simple upload, reducing effort and manual input. | Sarah Wierzbicki | Done |  | 3 | Sprint 2
NY4-55 | Call Backend from Frontend UI | User Story: * As a job seeker, I want my resume to be analyzed as soon as I upload it, so that I can begin swiping through job matches without delay. Acceptance Criteria: * The frontend calls the Flask backend /process-resume endpoint when a resume file is selected. * On success, a resumeID is saved to local storage for session tracking. * If successful, the user can navigate to the /search page to begin swiping. Benefit/Value: * Seamless integration ensures users can quickly move from upload to results, making the app feel fast and intuitive. | Eric Lantz | Done |  | 2 | Sprint 2
NY4-54 | Backend Query Job Dataset | User Story: * As a job seeker, I want the platform to match me with real job postings based on my resume, so that the recommendations I receive are relevant and up-to-date. Acceptance Criteria: * Backend connects to a structured dataset (CSV, database, or API) of job postings. * A function is implemented to retrieve relevant jobs based on skills, keywords, or embedding similarity. * Only verified or curated jobs are returned. * At least 20 jobs are returned per resume request. * Returned job objects include id, title, description, and metadata used by the frontend. Benefit/Value: * Provides users with trusted, personalized job options that feel meaningful, accurate, and current. | Sarah Wierzbicki | Done |  | 2 | Sprint 2
NY4-52 | Install Docker on EC2 Instance | As a developer, I want to have an installed Docker component on our EC2 instance. AC: A working docker on the Amazon EC2 Instance | Joseph Indriolo | Done |  | 1 | Sprint 1
NY4-50 | Provision MongoDB Table on EC2 Instance | As a developer, I need an MongoDB running on our Ec2 instance, so we can begin storing user data on it. AC: A working Ec2 instance that has MongoDB loaded on it. | Joseph Indriolo | Done |  | 1 | Sprint 1
NY4-49 | Deploy ML model to Sagemaker | User Story: * As a job seeker, I want accurate and fast job recommendations based on my resume, so that I can quickly discover relevant job opportunities. Acceptance Criteria: * The trained ML model is deployed as a SageMaker endpoint that accepts resume input and returns job recommendations. * The endpoint is accessible via a secure HTTP API. * The model returns predictions within 1 second for a typical resume file. * Model output includes a list of job IDs, match percentages, and any additional metadata used by the frontend. * Model uptime is monitored, and errors are logged or handled gracefully. Benefit/Value: * Ensures the intelligence of the platform is scalable and fast, allowing users to receive personalized recommendations without delays or errors. | Joseph Indriolo | Done |  | 2 | Sprint 2
NY4-48 | Cross browser testing | As a user, I should be able to visit and use the website from any browser without errors. AC: Ensure that ResuMInd works and looks correct across different common web browsers | Bushra, Ms. Anika | Done |  | 1 | Sprint 2
NY4-47 | Implement Form Inputs | User Story: * As a new user, I want to enter my name and upload my resume easily, so that I can quickly get started and receive job suggestions personalized to me. Acceptance Criteria: * The homepage includes a text input for name and a resume upload button. * The resume input accepts .pdf, .doc, and .docx files. * Upon selection, the file is stored and ready to be sent to the backend. * The name input can be optionally used to personalize UI text. Benefit/Value: * Smooth onboarding helps users feel confident and engaged right away, minimizing friction in beginning the job search process. | Bushra, Ms. Anika | Done |  | 1 | Sprint 2
NY4-46 | Design landing page | As a frontend developer, I want to build a landing page that is both informative and easy to navigate for users. | Bushra, Ms. Anika | Done | 02/Jul/25 9:48 AM;712020:bede8113-2cc2-4412-b29d-daf26a5ad715;[https://github.com/htmw/2025Su-NY4/pull/4¦https://github.com/htmw/2025Su-NY4/pull/4¦smart-link] | 1 | Sprint 1
NY4-43 | Develop ResuMind’s brand identity: | As a team, we want to align on defining ResuMind’s brand identity so that the design and tone are consistent across the site. AC: Documented brand tone | Bushra, Ms. Anika | Done | 02/Jul/25 4:05 PM;712020:bede8113-2cc2-4412-b29d-daf26a5ad715;AC: Document brand tone Document attached sharing the visual styling, who we serve, and identifying what makes us different. [^ResuMind Brand Identity.pdf] | 1 | Sprint 1
NY4-39 | Create end of possible swiping list item | User Story: * As a job seeker, I want to see a clear message when I’ve reviewed all available job postings, so that I know there are no more results to swipe and I’m not left waiting or confused. Acceptance Criteria: * When the job card deck is empty, a final static card or message is shown (e.g., “You’ve viewed all job postings for now!”). * The swipe buttons (thumbs up/down) are hidden or disabled when the deck is empty. * This state persists even after refresh, unless new jobs are added or the session is reset. * Optionally includes a button to “Start Over” or “Re-upload Resume”. Benefit/Value: * Prevents confusion or frustration by clearly communicating that there are no more jobs to swipe on, improving clarity and user experience at the end of a session. | Bushra, Ms. Anika | To Do |  | 1
NY4-37 | Ability to add tags to job postings | User Story: * As a job seeker, I want to add custom tags to job postings I’m interested in, so that I can easily organize, categorize, and filter them later based on my preferences. Acceptance Criteria: * On the Matches page, each job posting has a visible “Add Tag” or “Edit Tags” option. * Users can add multiple comma-separated tags (e.g., “Remote”, “Startup”, “Urgent”). * Tags are displayed with each job posting once saved. * Tags persist in local storage and remain after refresh or returning to the Matches page. * Users can filter job matches using a tag search bar to only view jobs containing a given tag. Benefit/Value: * This allows users to organize job postings based on their unique priorities, making it easier to compare options and streamline decision-making. | Eric Lantz | To Do |  | 1
NY4-36 | Create Undo last action option | User Story * As a job seeker, I want the ability to undo my last swipe action, so that I can recover from accidental swipes and reconsider my decision. AC: * After swiping left or right on a job, an “Undo” button appears for 5–10 seconds. * Clicking “Undo” restores the last swiped card to the top of the deck. * The restored card should not appear in the matched or rejected lists. * Only one level of undo is supported (cannot undo more than one previous swipe). * The undo action updates local storage accordingly (removes from matched or swipedLeftJobs if undone). Benefit/Value * This feature helps users recover from mistakes and ensures they don’t miss out on valuable opportunities due to accidental swipes, improving confidence and control over the job search process. | Eric Lantz | To Do |  | 1
NY4-34 | Create swipe left/right action | As a user, I want to swipe right to save a job for further review, so that I can revisit promising opportunities later. Swiping left removes it from the list. AC: When you swipe left, the job is removed from the list of jobs and when I swipe right, it adds the posting to a list that can be viewed. | Eric Lantz | Done | 30/Jun/25 7:10 PM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;[https://github.com/htmw/2025Su-NY4/pull/3¦https://github.com/htmw/2025Su-NY4/pull/3¦smart-link] | 1 | Sprint 1
NY4-33 | Create props for each part of the job application card | User Story: * As a job seeker, I want each job card to clearly display relevant job details (title, description, match score, etc.), so that I can make informed decisions while swiping. Acceptance Criteria: * The job card component accepts props for title, description, matchScore, and likelihood. * Props are dynamically populated from job data received from the backend. * Cards render correctly with various prop values and show placeholder text if a prop is missing. * The component is reusable across the swipe and matches pages. * A test card renders correctly with mock data during development. Benefit/Value: * Enables a scalable and flexible UI for showing personalized job information, helping users evaluate roles at a glance. | Eric Lantz | Done |  | 2 | Sprint 2
NY4-32 | Create right swiped job posting list | User Story: * As a job seeker, I want to view a list of all the job postings I swiped right on, so that I can revisit and apply to them later. Acceptance Criteria: * A dedicated “Matches” page displays all jobs that were swiped right. * Each job in the list shows: title, match percentage, and response likelihood. * The list is searchable by job title using a search input box. * The list is persisted in local storage and survives page refresh or session restart. * Each job entry includes a clearly visible “Apply Now” button (link placeholder for now). Benefit/Value: * This allows users to keep track of opportunities they’ve shown interest in, helping them organize their job search and return to matched jobs when ready to apply. | Eric Lantz | To Do |  | 2
NY4-31 | Create initial card component for job posting | As a developer, I want a card that is easy to read and has all the parts necessary to match the job applications that are being referenced on it. | Eric Lantz | Done | 30/Jun/25 1:16 PM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;Created basic card and deck components: [https://github.com/htmw/2025Su-NY4/pull/new/basic-card-and-deck-components¦https://github.com/htmw/2025Su-NY4/pull/new/basic-card-and-deck-components] | 1 | Sprint 1
NY4-30 | Create backend API using Flask | User Story: * As a job seeker, I want the app to process my uploaded resume and return job matches, so that I can get personalized recommendations without needing technical knowledge. Acceptance Criteria: * Flask API exposes an endpoint /process-resume that accepts file uploads via POST. * The uploaded resume is forwarded to the ML model and the results are returned in JSON format. * API response includes a resumeID and list of matched jobs. * CORS is enabled so the frontend can make cross-origin requests. * Returns appropriate status codes for success (200), client errors (400), or server errors (500). Benefit/Value: * This bridges the frontend and ML model, allowing users to submit resumes and receive recommendations without ever leaving the app. | Sarah Wierzbicki | Done |  | 1 | Sprint 1
NY4-29 | Research Deployment Methods | User Story: * As a developer working on ResuMind, I want to identify the best deployment strategy for the backend and ML model, so that users experience fast and reliable service. Acceptance Criteria: * At least 2 deployment methods are evaluated (e.g., AWS SageMaker, Lambda, EC2) * Each method is assessed for cost and integration with Flask. * Recommendations are documented clearly in a markdown or PDF report. * Team agrees on a method based on findings for MVP launch. Benefit/Value: * Ensures long-term stability and maintainability of the platform, improving the user experience and enabling smooth growth. | Joseph Indriolo | Done |  | 1 | Sprint 2
NY4-28 | Identify tool for front end design | As a frontend developer, I want to choose the best CSS tool so that our website is visually appealing and aligns with our design goals. AC: Document CSS tools and discuss with team. | Bushra, Ms. Anika | Done | 18/Jun/25 8:59 PM;712020:bede8113-2cc2-4412-b29d-daf26a5ad715;As a group, we decided that Material UI (MUI) is the best CSS tool to use for our project because it was specifically built for React, making it easy to integrate with our dev workflow. From a design perspective, it is also customizable which will help us create a professional and modern look for our site. Documentation attached: [^Selecting CSS Tool- Sprint 1.pdf] | 1 | Sprint 1
NY4-19 | Create test cases sheet | User Story: * As a developer, I want a centralized test case sheet that outlines how each feature will be tested, so that I can systematically verify functionality and ensure the app works as expected. Acceptance Criteria: * A test case sheet is created and shared with the team. * Test cases are written for the currently implemented user stories. * The sheet is stored in a shared location (shared drive). * The team has access and can contribute additional test cases as features are developed. Benefit/Value: * Provides a structured way to verify that user stories meet their acceptance criteria, reducing bugs and improving team confidence in the quality of the application | Bushra, Ms. Anika | Done |  | 2 | Sprint 2
NY4-18 | Work on job recommendation model | As a developer, I want figure out how to utilize huggingface semantic textual similarity in order to match users with proper job recommendations. AC: Documented findings on feasibility, and steps to execute, prerequisites. | Sarah Wierzbicki | Done |  | 2 | Sprint 1
NY4-17 | Clean job description data to be used for our database of jobs | As a developer I need to filter and clean our targeted datasource such that it is easier to read and use. AC: Dataset is filtered to meet our needs. | Sarah Wierzbicki | Done |  | 2 | Sprint 1
NY4-16 | Refine and complete high level architecture diagram | As a developer, I need to define a high level architecture diagram such that the flow of the software is clearly defined and socialized throughout the team. | Joseph Indriolo | Done |  | 2 | Sprint 1
NY4-15 | Begin developing code for resume parser | As a developer, I want to have a resume parser that will extract keywords from a given resume, used to train the needed models. AC: Finish training model on training dataset. | Sarah Wierzbicki | Done |  | 2 | Sprint 1
NY4-14 | Install needed frameworks on EC2 Instance | As a developer, I need to install the needed frameworks and technologies on the EC2 Instance such that we can host a back and front end on the machine. AC: Align with the team on what technologies are needed on The ec2 instance to support the application. Install the identified technologies on the machines. | Joseph Indriolo | Done | Possible Technologies: * Python * NVM NodeJS * Apache | 2 | Sprint 1
NY4-13 | Provision and Deploy Amazon EC2 Instance | As a developer, I need to provision an amazon EC2 instance such that we can deploy the front and back end to it. AC: Have a provisioned EC2 Instance ready for use. | Joseph Indriolo | Done |  | 2 | Sprint 1
NY4-12 | Identify the color scheme and design aspects of the frontend | As a user, I want to feel like the site is modern and interactive, not outdated with old looking UIs or boring colors/designs AC: Document and determine our brand identity, set component base. Align on frontend design patterns.Implement basic component structure. Basic template of Card and Resume Component. | Bushra, Ms. Anika | Done |  | 2 | Sprint 1
NY4-11 | Identify and install any additional react libraries needed for the frontend | As a developer, I need to see if there is any specific react libraries that would benefit our app, such as ones for swiping or cards. AC: Document a list of additional libraries that may be needed for ResuMind, share with team. | Eric Lantz | Done | 29/Jun/25 10:22 AM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;Need to install Framer-motion library for swiping of job postings: [https://github.com/htmw/2025Su-NY4/pull/new/Installed-framer-motion¦https://github.com/htmw/2025Su-NY4/pull/new/Installed-framer-motion] | 1 | Sprint 1
NY4-10 | Create react app for frontend development | As a developer, I want to create the file hierarchy needed for our frontend development AC: Have file structure created, running react app in local. | Eric Lantz | Done | 15/Jun/25 12:58 PM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;[https://github.com/htmw/2025Su-NY4/pull/1¦https://github.com/htmw/2025Su-NY4/pull/1¦smart-link] | 3 | Sprint 1
NY4-8 | Create Wikipage and insert Sprint 0 data into it |  | Eric Lantz | Done |  | 1 | Sprint 0
NY4-7 | Research and Define Technical Architecture | As a developer, I should have a clear and detailed architecture plan that will support the needs of the project. We should begin researching different cloud technologies that we will use for our infra. | Joseph Indriolo | Done |  | 1 | Sprint 0
NY4-6 | Hold Sprint 0 Retrospective |  | Joseph Indriolo | Done |  | 1 | Sprint 0
NY4-5 | Create Team Working Agreement | As a developer, I should clearly understand the contribution model within the team. Understanding meeting times, expectations and common practices. | Joseph Indriolo | Done |  | 1 | Sprint 0
NY4-4 | Create and define sprint deliverables | As a stakeholder I should have a clear schedule of what will happen in each sprint, and the intended deliverables at the end of the sprint. | Sarah Wierzbicki | Done |  | 1 | Sprint 0
NY4-3 | Create Technologies & Algorithms Slide | As a developer, I should understand clearly the technologies that are going to be used on this project. This includes the languages, frameworks and specific ML algorithms. | Sarah Wierzbicki | Done |  | 1 | Sprint 0
NY4-2 | Define Problem Statement & Project Description in Presentation | As a stakeholder I should understand the problem in which this software intends to solve. I should understand clearly what this project intends to accomplish. | Eric Lantz | Done |  | 1 | Sprint 0
NY4-1 | Create Personas for Presentation | As a stakeholder, I should be able to see and understand the potential customers whom in which our product could benefit. | Bushra, Ms. Anika | Done |  | 1 | Sprint 0