## Sheet 1 - Full Project Backlog
Full Project Backlog
Issue key | Issue id | Sprint | Summary | Description | Assignee | Status | Comments | Custom field (Story point estimate)
NY4-8 | 10007 | Sprint 0 | Create Wikipage and insert Sprint 0 data into it |  | Eric Lantz | Done |  | 1
NY4-7 | 10006 | Sprint 0 | Research and Define Technical Architecture | As a developer, I should have a clear and detailed architecture plan that will support the needs of the project. We should begin researching different cloud technologies that we will use for our infra. | Joseph Indriolo | Done |  | 1
NY4-6 | 10005 | Sprint 0 | Hold Sprint 0 Retrospective |  | Joseph Indriolo | Done |  | 1
NY4-5 | 10004 | Sprint 0 | Create Team Working Agreement | As a developer, I should clearly understand the contribution model within the team. Understanding meeting times, expectations and common practices. | Joseph Indriolo | Done |  | 1
NY4-4 | 10003 | Sprint 0 | Create and define sprint deliverables | As a stakeholder I should have a clear schedule of what will happen in each sprint, and the intended deliverables at the end of the sprint. | Sarah Wierzbicki | Done |  | 1
NY4-3 | 10002 | Sprint 0 | Create Technologies & Algorithms Slide | As a developer, I should understand clearly the technologies that are going to be used on this project. This includes the languages, frameworks and specific ML algorithms. | Sarah Wierzbicki | Done |  | 1
NY4-2 | 10001 | Sprint 0 | Define Problem Statement & Project Description in Presentation | As a stakeholder I should understand the problem in which this software intends to solve. I should understand clearly what this project intends to accomplish. | Eric Lantz | Done |  | 1
NY4-1 | 10000 | Sprint 0 | Create Personas for Presentation | As a stakeholder, I should be able to see and understand the potential customers whom in which our product could benefit. | Bushra, Ms. Anika | Done |  | 1
NY4-52 | 10275 | Sprint 1 | Install Docker on EC2 Instance | As a developer, I want to have an installed Docker component on our EC2 instance. AC: A working docker on the Amazon EC2 Instance | Joseph Indriolo | Done |  | 1
NY4-50 | 10273 | Sprint 1 | Provision MongoDB Table on EC2 Instance | As a developer, I need an MongoDB running on our Ec2 instance, so we can begin storing user data on it. AC: A working Ec2 instance that has MongoDB loaded on it. | Joseph Indriolo | Done |  | 1
NY4-46 | 10205 | Sprint 1 | Design landing page | As a frontend developer, I want to build a landing page that is both informative and easy to navigate for users AC: Completed landing/home page in Frontend code | Bushra, Ms. Anika | Done | 02/Jul/25 9:48 AM;712020:bede8113-2cc2-4412-b29d-daf26a5ad715;[https://github.com/htmw/2025Su-NY4/pull/4¦https://github.com/htmw/2025Su-NY4/pull/4¦smart-link] | 1
NY4-43 | 10202 | Sprint 1 | Develop ResuMind’s brand identity: | As a team, we want to align on defining ResuMind’s brand identity so that the design and tone are consistent across the site. AC: Documented brand tone | Bushra, Ms. Anika | Done | 02/Jul/25 4:05 PM;712020:bede8113-2cc2-4412-b29d-daf26a5ad715;AC: Document brand tone Document attached sharing the visual styling, who we serve, and identifying what makes us different. [^ResuMind Brand Identity.pdf] | 1
NY4-34 | 10129 | Sprint 1 | Create swipe left/right action | As a user, I want to swipe right to save a job for further review, so that I can revisit promising opportunities later. Swiping left removes it from the list. AC: When you swipe left, the job is removed from the list of jobs and when I swipe right, it adds the posting to a list that can be viewed. | Eric Lantz | Done | 30/Jun/25 7:10 PM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;[https://github.com/htmw/2025Su-NY4/pull/3¦https://github.com/htmw/2025Su-NY4/pull/3¦smart-link] | 1
NY4-31 | 10126 | Sprint 1 | Create initial card component for job posting | As a developer, I want a card that is easy to read and has all the parts necessary to match the job applications that are being referenced on it. | Eric Lantz | In Progress | 30/Jun/25 1:16 PM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;Created basic card and deck components: [https://github.com/htmw/2025Su-NY4/pull/new/basic-card-and-deck-components¦https://github.com/htmw/2025Su-NY4/pull/new/basic-card-and-deck-components] | 1
NY4-30 | 10093 | Sprint 1 | Create backend API using Flask | As a developer, I want figure out how to utilize an API using Flask to connect with our EC2 Instance and the frontend AC: A created API using Flask that connects to frontend code. | Joseph Indriolo | In Progress |  | 2
NY4-28 | 10059 | Sprint 1 | Identify tool for front end design | As a frontend developer, I want to choose the best CSS tool so that our website is visually appealing and aligns with our design goals. AC: Document CSS tools and discuss with team. | Bushra, Ms. Anika | Done | 18/Jun/25 8:59 PM;712020:bede8113-2cc2-4412-b29d-daf26a5ad715;As a group, we decided that Material UI (MUI) is the best CSS tool to use for our project because it was specifically built for React, making it easy to integrate with our dev workflow. From a design perspective, it is also customizable which will help us create a professional and modern look for our site. Documentation attached: [^Selecting CSS Tool- Sprint 1.pdf] | 1
NY4-18 | 10049 | Sprint 1 | Work on job recommendation model | As a developer, I want figure out how to utilize huggingface semantic textual similarity in order to match users with proper job recommendations. AC: Documented findings on feasibility, and steps to execute, prerequisites. | Sarah Wierzbicki | In Progress |  | 2
NY4-17 | 10048 | Sprint 1 | Clean job description data to be used for our database of jobs | As a developer I need to filter and clean our targeted datasource such that it is easier to read and use. AC: Dataset is filtered to meet our needs. | Sarah Wierzbicki | Done |  | 2
NY4-16 | 10047 | Sprint 1 | Refine and complete high level architecture diagram | As a developer, I need to define a high level architecture diagram such that the flow of the software is clearly defined and socialized throughout the team. | Joseph Indriolo | To Do |  | 2
NY4-15 | 10046 | Sprint 1 | Begin developing code for resume parser | As a developer, I want to have a resume parser that will extract keywords from a given resume, used to train the needed models. AC: Finish training model on training dataset. | Sarah Wierzbicki | Done |  | 2
NY4-14 | 10045 | Sprint 1 | Install needed frameworks on EC2 Instance | As a developer, I need to install the needed frameworks and technologies on the EC2 Instance such that we can host a back and front end on the machine. AC: Align with the team on what technologies are needed on The ec2 instance to support the application. Install the identified technologies on the machines. Possible Technologies: Python NVM NodeJS Apache | Joseph Indriolo | In Review |  | 2
NY4-13 | 10044 | Sprint 1 | Provision and Deploy Amazon EC2 Instance | As a developer, I need to provision an amazon EC2 instance such that we can deploy the front and back end to it. AC: Have a provisioned EC2 Instance ready for use. | Joseph Indriolo | Done |  | 2
NY4-12 | 10043 | Sprint 1 | Identify the color scheme and design aspects of the frontend | As a user, I want to feel like the site is modern and interactive, not outdated with old looking UIs or boring colors/designs AC: Document and determine our brand identity, set component base. Align on frontend design patterns.Implement basic component structure. Basic template of Card and Resume Component. | Bushra, Ms. Anika | In Progress |  | 2
NY4-11 | 10042 | Sprint 1 | Identify and install any additional react libraries needed for the frontend | As a developer, I need to see if there is any specific react libraries that would benefit our app, such as ones for swiping or cards. AC: Document a list of additional libraries that may be needed for ResuMind, share with team. | Eric Lantz | Done | 29/Jun/25 10:22 AM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;Need to install Framer-motion library for swiping of job postings: [https://github.com/htmw/2025Su-NY4/pull/new/Installed-framer-motion¦https://github.com/htmw/2025Su-NY4/pull/new/Installed-framer-motion] | 1
NY4-10 | 10041 | Sprint 1 | Create react app for frontend development | As a developer, I want to create the file hierarchy needed for our frontend development AC: Have file structure created, running react app in local. | Eric Lantz | Done | 15/Jun/25 12:58 PM;712020:cb4a141e-d501-421e-8a61-f01726e5ee5c;[https://github.com/htmw/2025Su-NY4/pull/1¦https://github.com/htmw/2025Su-NY4/pull/1¦smart-link] | 3
NY4-54 | 10277 |  | Create job matching module |  |  | To Do
NY4-53 | 10276 |  | Create text pre-processing module |  |  | To Do
NY4-51 | 10274 |  | Design ERD Database Diagram for ResuMind DB Capabilities |  | Joseph Indriolo | To Do
NY4-49 | 10240 |  | Deploy ML model to docker |  |  | To Do
NY4-48 | 10207 |  | Cross browser testing | As a frontend developer, I want to ensure that the site works across different browsers like Chrome and Safari | Bushra, Ms. Anika | To Do
NY4-47 | 10206 |  | Test form inputs | As a frontend developer, I want to ensure that forms are submitted successfully on the site. | Bushra, Ms. Anika | To Do
NY4-45 | 10204 |  | Define UI Theme | As a frontend developer, I want to apply a consistent theme across our site so that all components share a coherent look. | Bushra, Ms. Anika | To Do
NY4-44 | 10203 |  | Create visual style guide | As a frontend developer, I want to document all of the aesthetics for colors/typography used to ensure organization | Bushra, Ms. Anika | To Do
NY4-42 | 10169 |  | Create topic model for job matching |  |  | To Do
NY4-41 | 10136 |  | Create function to extract text from pdf/docs files |  |  | To Do
NY4-40 | 10135 |  | Verify backend to frontend connection works |  |  | To Do
NY4-39 | 10134 |  | Create end of possible swiping list item | As a user, I want to see a message if there are no more jobs to swipe through, so that I know when I’ve reached the end. | Eric Lantz | To Do
NY4-38 | 10133 |  | Create swipe card ability using npm library | As a user, I want to see an animation as I each swipe, so that I receive feedback that my action was successful. | Eric Lantz | To Do
NY4-37 | 10132 |  | Ability to add tags to job postings | As a user, I want to mark jobs as “applied,” “interviewing,” or “not yet applied,” so that I can track my job search progress. |  | To Do
NY4-36 | 10131 |  | Create Undo last action option | As a user, I want to undo my last swipe, so that I can recover a job if I swiped by mistake. |  | To Do
NY4-33 | 10128 |  | Create props for each part of the job application card |  |  | To Do
NY4-32 | 10127 |  | Create right swiped job posting list | As a user, I want each saved job to have a detailed view page, so that I can read the full job description and see application instructions. | Eric Lantz | To Do
NY4-29 | 10060 |  | Research Deployment Methods | As a developer we need to determine the best way to deploy the ML model such that it can be used by our frontend. AC: Documented findings on how backend ML model can be deployed to ec2 instance. |  | To Do |  | 1
NY4-19 | 10050 |  | Create test cases sheet | As a developer, I want to make sure all critical functionality is working as intended, and tracked for sprint end deliverables. AC: Testing steps documented, executed and recorded and shared with the team. All tests passing and feature working as intended. |  | To Do |  | 2